INSTITUTO TECNOLÓGICO Y DE ESTUDIOS SUPERIORES DE OCCIDENTE

Diseño de Sistemas Escalables

Equipo 1: Software Project Management Plan

Equipo:

Carlos Eduardo Félix Santamaría

Roman Gonzalez Gil

Bryan Edgardo Romo Gonzalez

Juan Pablo Quintero Corona

Profesor David Emmanuel Ramírez Tovar

05 de febrero de 2026

## 1. Introduction

The SPMP or Software Project Management Plan serves as a comprehensive guide for managing the planning, execution, and control of the project. Its purpose is to define the project’s objectives, scope, deliverables, organization, schedule, resources, and risk management strategies.

In outlining these elements, the SPMP ensures that all stakeholders share a common understanding of how the project will be managed and provides a structured framework to monitor progress, maintain quality, and achieve the desired outcomes efficiently.

### 1.1 Project Overview

Project:

This project consists of a property management system designed for closed communities (like condominiums, apartment complexes, and similar residential environments). The platform provides a centralized dashboard that allows property owners, administrators, and residents to efficiently manage daily operations, communication, and resources within the community.

Objective:

- Provide a centralized and intuitive dashboard for community management

- Simplify administrative tasks for property owners and administrators

- Improve communication between residents and management

- Offer residents easy access to relevant information and services

- Design a scalable, secure, and cloud-native system capable of supporting multiple communities

Main Deliverables:

- Fully functional responsive web application

- Management and control of condominiums

- User profile

- Technical and user documentation

Estimated Schedule: 4 months

Required Resources:

- 1 full-stack developer

- 1 software architect

- 1 project manager

- 1 QA

### 1.2 Project Deliverables

| Deliverable | Delivery Date | Location | Delivery Method | Quantity |
| --- | --- | --- | --- | --- |
| Configured Database | Month 1 | Database Server | Deploy script | 1 |
| Functional Web Application | Month 4 | Production Server | Automated deploy | 1 |
| Technical Documentation | Month 4 | Git Repository | Digital | 1 |
| Testing Plan | Month 4 | Dev Repository | Digital | 1 |

### 1.3 Evolution of the Software Project Management Plan

This document will evolve through the following expected phases:

| Version | Description | Expected Date |
| --- | --- | --- |
| Draft | Initial draft for team review | Week 1 |
| Preliminary | Revised version with initial team feedback | Week 2 |
| Revision 1 | First review after development begins | Month 1 |
| Revision 2 | Mid-development review | Month 3 |
| Final | Approved version after revisions | Month 4 |

## 2. Project Organization

### 2.1 Process Model

Development Model: Agile with 2-week iterations

Main Milestones:

- Setup and Architecture (Month 1)

- MVP – First Functional Version (Month 2)

- Complete Base Platform (Month 3)

- All Features Implemented (Month 4)

- Testing and Optimization (Month 4)

- Deployment and Launch (Month 4)

Main Work Products:

| Product | Planned Date | Change Control | Deliverable | Approvals |
| --- | --- | --- | --- | --- |
| System Architecture | Week 2 | Yes | No | Architect, Project Manager |
| UI/UX Design | Month 1 | Yes | Yes | Developer, Product Owner |
| Functional Prototype | Month 2 | Yes | Yes | Whole team |
| Implemented Features | Month 3 | Yes | No | Developer, Project Manager |
| Testing | Month 4 | Yes | Yes | QA |

### 2.2 Organizational Structure

Team Structure:

- Project Manager
 ├── Tech Lead (Developer)
 ├── QA Engineer
 └── Software Architect

### 2.3 Organizational Boundaries and Interfaces

Key Interfaces:

- Client/Stakeholders: Project Manager as main contact

- Marketing Team: For launch strategy

- Legal/Compliance: For terms of use and privacy

- IT Infrastructure: For hosting and deployment

### 2.4 Project Responsibilities

| Role | Main Responsibilities |
| --- | --- |
| Project Manager | Planning, monitoring, communication with stakeholders |
| Tech Lead | Visual design, prototyping, code review, user interface, player experience, responsive design, API, database |
| Software Architect | Technical architecture, technology decisions, business logic |
| QA Engineer | Testing, automation, quality control, security, user experience |

## 3. Managerial Process

### 3.1 Management Objectives and Priorities

Project Priorities:

- Quality: Smooth and bug-free user experience

- Functionality: Full implementation of planned features

- Schedule: Launch in 4 months

Management Philosophy:

- Iterative development with constant feedback

- Transparent and frequent communication

- Focus on user experience

### 3.2 Assumptions, Dependencies, and Constraints

Assumptions:

- The team has experience with modern web technologies

- Users will have access to modern browsers

- No special licenses are required for specific technologies

Dependencies:

- Availability of the complete team from the start

- Access to hosting services

- Stakeholder approval of designs

Constraints:

- Compliance with privacy regulations (GDPR)

### 3.3 Risk Management

Risk Management:

- Bi-weekly risk review in sprint meetings

- Mitigation strategies defined for each high-risk item

Main Identified Risks:

- Development delays due to technical complexity

- Performance issues on mobile devices

- Competition in the market

### 3.4 Monitoring and Controlling Mechanisms

Monitoring Mechanisms:

- Status Reports: Bi-weekly with progress metrics

- Meetings: Sprint reviews

- Key Metrics: Team velocity, burn-down charts, testing coverage

- Tools: Jira/Trello for tracking, Git for version control

### 3.5 Staffing Plan

Staffing Plan:

| Role | Quantity | Start | Duration | Required Skills |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | Day 1 | 4 months | Agile, communication, management |
| Tech Lead | 1 | Day 1 | 4 months | Architecture, technical leadership |
| Frontend Developer | 1 | Day 1 | 4 months | HTML/CSS/JS |
| Backend Developer | 1 | Day 1 | 4 months | Python, AWS Lambda, DynamoDB |
| UI/UX Designer | 1 | Day 1 | 4 months | Figma, web design, UX |
| QA Engineer | 1 | Month 2 | 2 months | Automated testing, QA |

## 4. Technical Process

### 4.1 Methods, Tools, and Techniques

Development Environment:

- Frontend: HTML / CSS / JavaScript (hosted on Amazon S3 + CloudFront)

- Backend: Python 3.10 (AWS Lambda)

- Database: Amazon DynamoDB (Pay-Per-Request)

- Hosting: AWS

- Version Control: Git + GitHub

Development Tools:

- IDE: Visual Studio Code

- Design: Figma

- Project Management: Notion

- Communication: WhatsApp

- CI/CD: GitHub Actions

Methodologies:

- Agile development

- Mandatory code reviews

### 4.2 Software Documentation

Documents to be Developed:

- Software Requirements Specification (SRS)

- Software Design Document

- Code Style Guide

- API Documentation

- Software Test Description

- Deployment Guide

### 4.3 Project Support Functions

Support Functions:

- Configuration Control: Git workflows, branching strategy

- Quality Assurance: Unit testing

- Documentation: API documentation, code comments

## 5. Work Packages, Schedule, and Budget

### 5.1 Work Packages

WP1: Project Setup (Weeks 1-2)

- Development environment setup

- Repository configuration

- Architecture definition

WP2: Design and Prototyping (Weeks 2-4)

- UI/UX design

- Interactive prototype

- Stakeholder validation

WP3: Base Infrastructure (Weeks 5-6)

- Database setup

- Basic API

- Authentication system

- First features

WP4: Feature Development (Weeks 6-12)

- Implementation of all features

- Individual testing

- Platform integration

WP5: Testing and deployment (Weeks 13-14)

- System-wide testing

- Bug fixes

- Production setup

- Final deployment

### 5.2 Dependencies

- WP2 depends on completion of WP1

- WP4 requires WP3 completion

- WP5 cannot start until WP4 is complete

### 5.3 Resource Requirements

Resources per Month:

- Personnel: 4 full-time people

- Hardware: Development laptops, testing servers

- Software: Development tool licenses

- Infrastructure: Services for development and testing

### 5.4 Budget and Resource Allocation

Budget Distribution:

- Team salaries: 70%

- Infrastructure and hosting: 15%

- Tools and licenses: 10%

- Contingency: 5%

### 5.5 Schedule

Main Timeline:

- Month 1: Setup and initial design

- Month 2: Infrastructure and first features

- Month 3-4: Remaining feature development

- Month 4: Testing and optimization

- Month 4: Deployment and launch

## 6. Additional Components

Marketing and Launch

- Digital marketing plan

- Social media strategy

- User acquisition plan

Post-Launch Maintenance

- Technical support plan

- Update strategy

- Monitoring and analytics

Scalability

- Monetization strategy

- Native mobile expansion

## 7. Appendices

- Appendix A: Meeting Minutes Log

Sprint 1: (Week 1 - 2)

Expected Progress (WP1):

- Development environment setup.

- Repository configuration.

- Initial documentation.

Recorded Progress: The project initiation phase was successfully completed. We established a centralized version control system using a GitHub repository and configured the development environments for both frontend and backend teams. Preliminary documentation was drafted, including communication protocols and shared collaborative folders. This setup ensured that all team members had access to the necessary tools and architectural guidelines before the development of core features began.

Sprint 2: (Week 3 - 4)

Expected Progress (WP2):

- Architecture definition.

- Requirements definition.

- Design and Prototyping.

Recorded Progress: The system architecture was defined in detail, focusing on a serverless approach using AWS Lambda and DynamoDB to ensure scalability. We finalized the requirements gathering process by conducting meetings with stakeholders and deriving functional specifications from the technical architecture. Additionally, the UI/UX design phase commenced with the creation of interactive prototypes, establishing the visual layout for the login, registration, and management modules.

Sprint 3: (Week 5 - 6)

Expected Progress (WP3):

- Database setup (DynamoDB).

- Basic API implementation.

- Authentication system.

- First core features.

Recorded Progress: The core infrastructure was successfully deployed. We implemented the NoSQL schema using Amazon DynamoDB, establishing tables for Users, Condos, and Units. The authentication system was finalized using JWT (JSON Web Tokens) for secure session management and Bcrypt for password hashing. Initial API endpoints were integrated with Lambda functions, allowing for the first successful communication between the frontend and the cloud backend.

Sprint 4: (Week 7 - 8)

Expected Progress (WP4 - Phase 1):

- Implementation of Condominium and Unit management.

- S3 integration for image storage.

- Initial unit testing.

Recorded Progress: Significant progress was made in functional modules. We implemented the CRUD logic for Condominium Management and Residential Unit registration. Integration with Amazon S3 was completed to handle the storage of condominium photos and documentation. Unit tests were introduced using Jest for the frontend and Pytest for the backend handlers, ensuring that the creation of resources follows the established business rules and validation constraints.

Sprint 5: (Week 9 - 10)

Expected Progress (WP4 - Phase 2):

- Maintenance Fee Management.

- Incident Management system.

- State transition logic.

Recorded Progress: The financial and operational modules were integrated. We developed the Maintenance Fee system, including automated fee generation and payment status tracking. Simultaneously, the Incident Management system was deployed, allowing residents to report issues and admins to assign maintenance staff. We applied a Deterministic Finite Automaton (DFA) model to validate the state transitions of these processes, ensuring the system remains scalable and consistent under concurrent operations.

Sprint 6: (Week 11 - 12)

Expected Progress (WP4 - Phase 3):

- Announcements and Notifications.

- Platform integration.

- Final feature implementation.

Recorded Progress: The Announcement module was completed, enabling administrative broadcasts with automated archiving and timestamping. All remaining features, including amenity reservations and user profile management, were fully integrated into the platform. We conducted a final review of the API Gateway configurations to ensure all endpoints are properly protected by the JWT authorization layer.

Sprint 7: (Week 13 - 14)

Expected Progress (WP5):

- System-wide testing.

- Bug fixes.

- Production setup and final deployment.

Recorded Progress: A comprehensive testing phase was executed, achieving an overall code coverage of 79-80%. Integration tests using Moto were performed to simulate the AWS environment, identifying and resolving critical bugs in the reservation conflict logic. The production environment was provisioned, and the final version of the system was deployed. Documentation was updated to include the Software Test Plan (STP) and the final deployment architecture.

Diagram: